## Slide 1: SOFTWARE ENGINEERING
Week 4
Software Project Management

## Slide 2: Agenda
Project Management Concepts
Project Planning
Estimation
Process Metrics
Quality Management

## Slide 3: Planning
Project Management Concepts
Estimation
Planning
Management

## Slide 4: Project Planning
Planning techniques, includes the following activities
  Identify and organize resources (e.g. team, hardware) required for the project
  Develop a work breakdown structure (WBS) and identify packages for the tasks in the work breakdown structure(WBS)
  Define a schedule of objectively measurable milestones organized as a GANTT chart
  Prepare a schedule network and identify the critical path(s)
Planning activities should be continuously held during the project as a rolling wave

## Slide 5: Team Planning
3. Planning
3.1. Team Planning
3.2. Task Planning
3.3. Time Planning

## Slide 6: Software Teams
The following factors must be considered when selecting a software project team structure
  the difficulty of the problem to be solved
  the size of the resultant program(s) in lines of code or function points
  the time that the team will stay together (team lifetime)
  the degree to which the problem can be modularized
  the required quality and reliability of the system to be built
  the rigidity of the delivery date
  the degree of sociability (communication) required for the project

## Slide 7: Team Organizations
There exist two main types of organizational structures:
  Hierarchical organization: All the people associated with a project are grouped into functional departments that report directly within the vertical line of command.
  Matrix organization: People are grouped based on the functions they perform.
Also based on the location of the project personnel, teams may be:
  Centralized
  Distributed
    Globally distributed
  Mixed
Small software engineering groups are usually organised informally without a rigid structure.
For large projects, there may be a hierarchical structure where different groups are responsible for different sub-projects.

## Slide 8: Team Organizations

## Slide 9: An Example Team Organization

## Slide 10: An Example Team Organization

## Slide 11: Team Organizations

## Slide 12: Agile Teams
Agile teams have the following characteristics
Co-location
Engaged Customers
Self-Organizing
Accountable and Empowered
Cross-Functional
Tips for Forming Your Agile Team
Look for Generalists
People Who Are Comfortable with Ambiguity
Team Players Who Can Check Their Egos at the Door

## Slide 13: Task Planning
3. Planning
3.1. Team Planning
3.2. Task Planning
3.3. Time Planning

## Slide 14: Task Planning
In order to work your way down in decomposition towards atomic tasks, you need to come up with an architectural decomposition.
Architectural design of software is concerned with specifying the software modules, their interrelationships, and their connections to the environment of the software.
We will examine Software Architectures in detail later. But let’s work on a trivial ATM software example to illustrate how we obtain WBS.

## Slide 15: Task Planning
Some prioritized requirements for ATM software
Essential requirements
  E1 Financial transactions shall be authorized by an ATM card and a password
  E2 Financial transactions shall be terminated if a customer fails to enter the correct password « settable » times
  E3 Financial transaction shall allow quick cash withdrawals
  E4 Financial transaction shall provide a printed receipt for each transaction
  E5 The ATM shall retain the information listed in the requirements specification, for each customer transaction
  E6 Financial transaction shall process Terminate requests from customers

## Slide 16: Task Planning
Some prioritized requirements for ATM software
Desirable requirements
  D1 Financial transaction should accommodate balance inquiry transactions
  D2 Financial transaction should accommodate standard withdrawal transactions
  D3 Financial transaction should accommodate deposit transactions
  D4 Customers should be allowed to conduct multiple transactions per session
Optional requirements
  O1 Financial transaction could support debit card transactions
  O2 Financial transaction could support payment of utility bills
  O3 Financial transaction could allow customers to purchase postage stamps which will be disbursed by the ATM hardware

## Slide 17: Task Planning

## Slide 18: Task Planning - WBS

## Slide 19: Task Planning – Task Extraction
Following WBS construction, tasks should be extracted to build a time plan and assign to resources(team). Tasks can also be assigned story points and can be used in estimation and tracking for agility.

## Slide 20: Time Planning
3. Planning
3.1. Team Planning
3.2. Task Planning
3.3. Time Planning

## Slide 21: Effort and Delivery Time
Putnam–Norden–Rayleigh (PNR) Curve

## Slide 22: For Scheduling
PERT Chart:
  Shows the relationships based on tasks or activities
  Defines tasks that can be done concurrently or not and critical path
Gantt Chart:
  Shows schedule (timeline) information for each task as a bar chart

## Slide 23: PERT Chart
Project Evaluation and Review Technique
Also known as Task Network Diagram
  Nodes: activities / tasks and estimated duration
  Edges: dependencies
Critical path: Longest path from start to finish. Any slippage on the critical path will cause project delay.

## Slide 24: PERT Example : Tasks and Durations
TASKS | WEEKS
1.2 Software Development | 11
1.2.1 Requirements Analysis | 3
1.2.2 Architectural Design | 2
1.2.3 Procedural Design | 2.5
1.2.4 Code | 3.5
1.3 Testing | 7
1.3.1 Unit Test | 3
1.3.2 Integration Test | 4
1.3.3 Acceptance Test | 1
1.4 Operations | 5
1.4.1 Packaging | 1
1.4.2 Customer Training | 5

## Slide 25: PERT Chart

## Slide 26: GANTT Chart
Also known as timeline chart
Shows high level view of whole project
  Horizontal bars show duration of tasks
  Triangles show milestones
  Vertical lines show dependencies

## Slide 27: An example
Let’s assume we identify the following tasks

## Slide 28: An example
Following milestones can be extracted

## Slide 29: An example
Sometimes a task network is constructed to identify critical paths.

## Slide 30: An example
A final remark is to identify dependencies and pay attention to workloads

## Slide 31: Project Plans
In a plan-driven development project, a project plan sets out the resources available to the project, the work breakdown and a schedule for carrying out the work.
Plan sections
  Introduction
  Project organization
  Risk analysis
  Hardware and software resource requirements
  Work breakdown
  Project schedule
  Monitoring and reporting mechanisms

## Slide 32: A Typical Software Project Plan Document
1. Introduction
A. Purpose of Plan
B. Project Scope and Objectives
2. Project Estimates
A. Historical Data Used for Estimates
B. Estimation Techniques
C. Estimates of Effort, Cost, Duration
3. Risks Management Strategy
A. Risk Table
B. Discussion of Risks to be Managed
C. RMMM Plan
4. Schedule
A. Project Work Breakdown Structure
B. Task Network
C. Timeline Chart
D. Resource Table
5. Project Resources
A. People
B. Hardware and Software
C. Special Resources
6. Staff Organization
A. Team Structure
B. Management Reporting
7. Tracking and Control Mechanisms
A. Quality Assurance and Control
B. Change Management and Control
8. Appendices

## Slide 33: Risk Management
4. Management
4.1. Risk Management
4.2. Quality Management
4.3. Change Management

## Slide 34: Risk Estimation
Risk projection, also called risk estimation, attempts to rate each risk in two ways
  the likelihood or probability that the risk is real
  the consequences of the problems associated with the risk, should it occur.
The are four risk projection steps:
    establish a scale that reflects the perceived likelihood of a risk
    delineate the consequences of the risk
    estimate the impact of the risk on the project and the product,
    note the overall accuracy of the risk projection so that there will be no misunderstandings.

## Slide 35: Risk Table
Risks | Category | Probability % | Impact | Remedy Plan
Size estimate may be significantly low | PS | 60 | 2 | 
Larger number of users than planned | PS | 30 | 3 | 
Less reuse than planned | PS | 70 | 2 | 
End users resist system | BU | 40 | 3 | 
Delivery deadline will be tightened | BU | 50 | 2 | 
Funding will be lost | CU | 40 | 1 | 
Customer will change requirements | PS | 80 | 2 | 
Technology will not meet expectations | TE | 30 | 1 | 
Lack of training on tools | TE | 60 | 3 | 
Staff inexperienced | ST | 30 | 2 | 
Staff turnover will be high | ST | 60 | 2 | 
. . . . . . . |  |  |  | 
Sort the table by probability and impact
Cut-off low probability risks

## Slide 36: Examples of Different Risk Types
Risk type | Possible risks
Technology | The database used in the system cannot process as many transactions per second as expected. (1) Reusable software components contain defects that mean they cannot be reused as planned. (2)
People | It is impossible to recruit staff with the skills required. (3) Key staff are ill and unavailable at critical times. (4) Required training for staff is not available. (5)
Organizational | The organization is restructured so that different management are responsible for the project. (6) Organizational financial problems force reductions in the project budget. (7)
Tools | The code generated by software code generation tools is inefficient. (8) Software tools cannot work together in an integrated way. (9)
Requirements | Changes to requirements that require major design rework are proposed. (10) Customers fail to understand the impact of requirements changes. (11)
Estimation | The time required to develop the software is underestimated. (12) The rate of defect repair is underestimated. (13) The size of the software is underestimated. (14)

## Slide 37: Risk Impact
The overall risk exposure, RE, is determined using the following relationship
RE = P x C
where
  P is the probability of occurrence for a risk
  C is the cost to the project should the risk occur

## Slide 38: Risk Impact Example
Risk identification. Only 70 percent of the software components scheduled for reuse will, in fact, be integrated into the application. The remaining functionality will have to be custom developed.
Risk probability. 80% (likely).
Risk impact. 60 reusable software components were planned. If only 70 percent can be used, 18 components would have to be developed from scratch (in addition to other custom software that has been scheduled for development). Since the average component is 100 LOC and local data indicate that the software engineering cost for each LOC is $14.00, the overall cost (impact) to develop the components would be 18 x 100 x 14 = $25,200.
Risk exposure. RE = 0.80 x 25,200 ~ $20,200.

## Slide 39: Risk Mitigation, Monitoring, Management
Risk Mitigation,Monitoring,Management (RMMM)
Mitigation : how can we avoid the risk?
Monitoring : what factors can we track that will enable us to determine if the risk is becoming more or less likely?
Management :what contingency plans do we have if the risk becomes a reality?

## Slide 40: Examples of common risks
Risk | Affects | Description
Staff turnover | Project | Experienced staff will leave the project before it is finished.
Management change | Project | There will be a change of organizational management with different priorities.
Hardware unavailability | Project | Hardware that is essential for the project will not be delivered on schedule.
Requirements change | Project and product | There will be a larger number of changes to the requirements than anticipated.
Specification delays | Project and product | Specifications of essential interfaces are not available on schedule.
Size underestimate | Project and product | The size of the system has been underestimated.
CASE tool underperformance | Product | CASE tools, which support the project, do not perform as anticipated.
Technology change | Business | The underlying technology on which the system is built is superseded by new technology.
Product competition | Business | A competitive product is marketed before the system is completed.

## Slide 41: Quality Management and Metrics
4. Management
4.1. Risk Management
4.2. Quality Management
4.3. Change Management

## Slide 42: Why Do We Measure?
measurement
What do we
use as a
basis?
• size?
• function?
project metrics
process metrics
process
product
product metrics

## Slide 43: Why Do We Measure?
assess the status of an ongoing project
track potential risks
uncover problem areas before they go “critical,”
adjust work flow or tasks,
evaluate the project team’s ability to control quality of software work products.

## Slide 44: Software Process Improvement
SPI
Process model
Improvement goals
Process metrics
Process improvement
recommendations

## Slide 45: Typical Project Metrics
Effort/time per software engineering task
Errors uncovered per review hour
Scheduled vs. actual milestone dates
Changes (number) and their characteristics
Distribution of effort on software engineering tasks
Examples:
total FP estimation (Function Points)
total LOC estimation (Lines of Code)
FP per person-month
LOC per person-month
errors or defects per KLOC (thousand LOC)
pages of documentation per KLOC

## Slide 46: Object-Oriented Metrics
Number of scenario scripts (use-cases)
Number of support classes (required to implement the system but are not immediately related to the problem domain)
Average number of support classes per key class (analysis class)
Number of subsystems (an aggregation of classes that support a function that is visible to the end-user of a system)

## Slide 47: Web Project Metrics
Number of static Web pages (the end-user has no control over the content displayed on the page)
Number of dynamic Web pages (end-user actions result in customized content displayed on the page)
Number of internal page links (internal page links are pointers that provide a hyperlink to some other Web page within the WebApp)
Number of persistent data objects
Number of external systems interfaced
Number of static content objects
Number of dynamic content objects
Number of executable functions

## Slide 48: Change Management
4. Management
4.1. Risk Management
4.2. Quality Management
4.3. Change Management

## Slide 49: What are changes?
Changes in
business requirements
Changes in
technical requirements
Data
Other
documents
Code
Test
Project
Plan
Changes in
user requirements
software models

## Slide 50: Terminology
Term | Explanation
Configuration item or software configuration item (SCI) | Anything associated with a software project (design, code, test data, document, etc.) that has been placed under configuration control. There are often different versions of a configuration item. Configuration items have a unique name.
Configuration control | The process of ensuring that versions of systems and components are recorded and maintained so that changes are managed and all versions of components are identified and stored for the lifetime of the system.
Version | An instance of a configuration item that differs, in some way, from other instances of that item. Versions always have a unique identifier, which is often composed of the configuration item name plus a version number.
Baseline | A baseline is a collection of component versions that make up a system. Baselines are controlled, which means that the versions of the components making up the system cannot be changed. This means that it should always be possible to recreate a baseline from its constituent components.
Codeline | A codeline is a set of versions of a software component and other configuration items on which that component depends.

## Slide 51: Terminology - II
Term | Explanation
Mainline | A sequence of baselines representing different versions of a system.
Release | A version of a system that has been released to customers (or other users in an organization) for use.
Workspace | A private work area where software can be modified without affecting other developers who may be using or modifying that software.
Branching | The creation of a new codeline from a version in an existing codeline. The new codeline and the existing codeline may then develop independently.
Merging | The creation of a new version of a software component by merging separate versions in different codelines. These codelines may have been created by a previous branch of one of the codelines involved.
System building | The creation of an executable system version by compiling and linking the appropriate versions of the components and libraries making up the system.

## Slide 52: Versioning
During maintenance, at all times there are at least two versions of the product:the old version, and the new version
There are two types of versions: revisions and variations
Revisions:
  A version to fix a fault in the artifact
  We cannot throw away an incorrect version
    The new version may be no better
    Some sites may not install the new version
  Perfective and adaptive maintenance also result in revisions

## Slide 53: Variations
Variations:
  A variation is a version for a different operating system
  Variations are designed to coexist in parallel

## Slide 54: Baseline Versioning

## Slide 55: Configuration-Control Tools
Configuration-Control Tools
  Gradle
  Maven
  Build.NET
Versioning Tools
  CVS
  SVN
  GIT
Other commercial tools
  TFS (Microsoft)
  ClearCase (IBM Rational Software)

## Slide 56: Wrap-up
This week we present
Project Estimation: How to forecast about the project before the project goes underway
Project Planning: What kind of activities should be perform to organize the project resources-activities in a plan-driven way
Project Management: How can we measure-monitor-assess various indicators of project progress

## Slide 57: Next Week
We will introduce various techniques and contemporary issues in Requirements Engineering!!!